## Team Members
Team Member | Period Start Date | Period End Date | Allocation % | Expected Hours in TTS | Actual Hours in TTS | Less Hrs in TTS?
Amit Khera | 2019-01-26 | 2019-02-22 | 100% | 180 | 180 | NO
Amritpreet Singh | 2019-01-26 | 2019-02-22 | 100% | 180 | 180 | NO
Neha Venugopal | 2019-02-04 | 2019-02-22 | 100% | 135 | 135 | NO
Nidhi Singh | 2019-01-26 | 2019-02-22 | 100% | 180 | 180 | NO
Nikita Arunabh | 2019-01-26 | 2019-02-22 | 100% | 180 | 188 | NO
Rikki Bindra | 2019-01-26 | 2019-02-22 | 25% | 45 | 93 | NO
Formulas:
Expected Hours in TTS = [Allocation %]*NETWORKDAYS([Period Start Date],[Period End Date])*9

## TTS Extract
Date | TeamMember | project | Module | Phase | Activity | Description | Ref. ID/Ticket ID | TotalHrs | HrsMins
2019-02-01 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | BREXIT - workstation changes - venue on Blotter | BREXIT-3 | 3 | 3:00
2019-02-01 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | BREXIT - workstation changes - venue on Blotter | BREXIT-3 | 3 | 3:00
2019-02-01 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | BREXIT - workstation changes - venue on Blotter | BREXIT-3 | 3 | 3:00
2019-01-02 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | Include GBP / EUR SAS in â€™GBP and EUR Bondâ€™ bucket for AutoEx | 107758 | 1 | 1:00
2019-01-02 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Suppress Disclosed Axe Alerts Option | 109935 | 8 | 8:00
2019-01-03 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | Suppress Disclosed Axe Alerts Option | 109935 | 2 | 2:00
2019-01-03 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Suppress Disclosed Axe Alerts Option | 109935 | 2.5 | 2:30
2019-01-03 | Amit Khera | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Nidhi's system setup | N/A | 4.5 | 4:30
2019-02-04 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | BREXIT - code review of Venue column on Blotter | BREXIT-3 | 1 | 1:00
2019-02-04 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | BREXIT - Venue column on Blotter | BREXIT-3 | 4 | 4:00
2019-02-04 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | BREXIT - Venue column on Blotter | BREXIT-3 | 4 | 4:00
2019-01-04 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | Suppress Disclosed Axe Alerts Option | 109935 | 2 | 2:00
2019-01-04 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Suppress Disclosed Axe Alerts Option | 109935 | 2.5 | 2:30
2019-01-04 | Amit Khera | MKTX_Trading Platform Development | General | Project Transition/KT | KT Tasks | KT to Nidhi | N/A | 4.5 | 4:30
2019-02-05 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | BREXIT - Venue filter on Blotter | BREXIT-3 | 9 | 9:00
2019-02-06 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | BREXIT - code review of Negotiation screen, Trade ticket | BREXIT-2 | 1 | 1:00
2019-02-06 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | BREXIT - Venue filter on Blotter | BREXIT-3 | 8 | 8:00
2019-02-07 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | BREXIT - code review of Print Trade ticket, Trade Alert | BREXIT-2 | 1 | 1:00
2019-02-07 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | BREXIT - code review of Venue filter on Blotter, AC | BREXIT-3 | 1 | 1:00
2019-02-07 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | BREXIT - Venue filter on Blotter | BREXIT-3 | 7 | 7:00
2019-01-07 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | Suppress Disclosed Axe Alerts Option | 109935 | 2 | 2:00
2019-01-07 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Suppress Disclosed Axe Alerts Option | 109935 | 7 | 7:00
2019-02-08 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | BREXIT - MIFID2 panel on Inquiry List screen | BREXIT-5 | 4.5 | 4:30
2019-02-08 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | BREXIT - MIFID2 panel on Inquiry List screen | BREXIT-5 | 4.5 | 4:30
2019-01-08 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 9 | 9:00
2019-01-09 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 2 | 2:00
2019-01-09 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 7 | 7:00
2019-01-10 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 9 | 9:00
2019-02-11 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | MIFID2 panel changes for Inquiry List | BREXIT-5 | 4.5 | 4:30
2019-02-11 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | MIFID2 panel changes for Inquiry List | BREXIT-5 | 4.5 | 4:30
2019-01-11 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 2 | 2:00
2019-01-11 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 7 | 7:00
2019-02-12 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | MIFID2 panel changes for Inquiry List | BREXIT-5 | 4.5 | 4:30
2019-02-12 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | MIFID2 panel changes for Inquiry List | BREXIT-5 | 4.5 | 4:30
2019-02-13 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | MIFID2 panel changes for Inquiry List | BREXIT-5 | 2 | 2:00
2019-02-13 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | MIFID2 panel changes for Inquiry List | BREXIT-5 | 7 | 7:00
2019-02-14 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Default user platform derivation | BREXIT-6 | 4.5 | 4:30
2019-02-14 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | Default user platform derivation | BREXIT-6 | 4.5 | 4:30
2019-01-14 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 9 | 9:00
2019-02-15 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | Default user platform derivation | BREXIT-6 | 2 | 2:00
2019-02-15 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Default user platform derivation | BREXIT-6 | 7 | 7:00
2019-01-15 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 2 | 2:00
2019-01-15 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 7 | 7:00
2019-01-16 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 7 | 7:00
2019-01-16 | Amit Khera | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Nikita's system setup. | N/A | 2 | 2:00
2019-01-17 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 2 | 2:00
2019-01-17 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Make the USHG protocol dealer submit flow just like USHY or EM Price. | 110595 | 5 | 5:00
2019-01-17 | Amit Khera | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Nikita's system setup. | N/A | 2 | 2:00
2019-02-18 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | Default user platform derivation | BREXIT-6 | 4.5 | 4:30
2019-02-18 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Default user platform derivation | BREXIT-6 | 4.5 | 4:30
2019-01-18 | Amit Khera | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Nikita's system setup. | N/A | 2 | 2:00
2019-01-18 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | BREXIT â€“ Division of MKTX_EU (Europe) into MKTX_UK (UK) and MKTX_NL (Netherlands). | N/A | 7 | 7:00
2019-02-19 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Listing/Delisting/Relisting of new MTF (MANL) | 111110 | 4.5 | 4:30
2019-02-19 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Listing/Delisting/Relisting of new MTF (MANL) | 111110 | 4.5 | 4:30
2019-02-20 | Amit Khera | MKTX_Trading Platform Development | General | Integration & System Testing | Re-testing | Fixing forward integration into 10.3.0 issues | BREXIT-1 | 9 | 9:00
2019-02-21 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | Hiding alerts for Disclosed Axes posted by dealers | 110119 | 1 | 1:00
2019-02-21 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | Refactoring MIFIDUtils.fetchDefaultUserPlatform() | BREXIT-8 | 1 | 1:00
2019-02-21 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | Refactoring MIFIDUtils.fetchDefaultUserPlatform() | BREXIT-8 | 1 | 1:00
2019-02-21 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Refactoring MIFIDUtils.fetchDefaultUserPlatform() | BREXIT-8 | 3 | 3:00
2019-02-21 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Refactoring MIFIDUtils.fetchDefaultUserPlatform() | BREXIT-8 | 3 | 3:00
2019-01-21 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | BREXIT changes - division of MKTX_EU into MKTX_UK and MKTX_NL. | BREXIT | 9 | 9:00
2019-02-22 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | Listing/Delisting/Relisting of new MTF (MANL) | 111110 | 2 | 2:00
2019-02-22 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Listing/Delisting/Relisting of new MTF (MANL) | 111110 | 7 | 7:00
2019-01-22 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | BREXIT changes - division of MKTX_EU into MKTX_UK and MKTX_NL. | BREXIT | 9 | 9:00
2019-01-23 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | BREXIT changes - division of MKTX_EU into MKTX_UK and MKTX_NL. | BREXIT | 9 | 9:00
2019-01-24 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | BREXIT changes - division of MKTX_EU into MKTX_UK and MKTX_NL. | BREXIT | 9 | 9:00
2019-01-25 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | BREXIT changes - division of MKTX_EU into MKTX_UK and MKTX_NL. | BREXIT-1 | 9 | 9:00
2019-01-28 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-28 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-28 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-29 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Coding | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-29 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-29 | Amit Khera | MKTX_Trading Platform Development | General | Requirement | Analysis & documentation | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-30 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-30 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-30 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | BREXIT - workstation changes - single inquiry window | BREXIT | 3 | 3:00
2019-01-31 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-31 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-01-31 | Amit Khera | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | BREXIT - workstation changes - single inquiry window | BREXIT-1 | 3 | 3:00
2019-02-01 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | doing client side code changes. | 110119 | 8 | 8:00
2019-02-01 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | scheduled a code review meeting with Chandan and Andrew for reviewing the fix related to backfilling â€˜Axeâ€™ watchlist option at GoLive. | 109935 | 1 | 1:00
2019-01-02 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | review done | N/A | 2 | 2:00
2019-01-02 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | code rework done | N/A | 5 | 5:00
2019-01-02 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | would coordinate with Marvin for Munis Axe setup, as Munis Axe also needs to be tested under this requirement. | N/A | 2 | 2:00
2019-01-03 | Amritpreet Singh | MKTX_Trading Platform Development | General | Integration & System Testing | Requirements Review/Analysis | working to bring the Muni bonds into the system/setup so that he may test Munis Axe. | N/A | 9 | 9:00
2019-02-04 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | Code rework done | 108825 | 4 | 4:00
2019-02-04 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | completed client side code changes | 110119 | 5 | 5:00
2019-01-04 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | The testing of Axe for a Muni bond failed today. Looking further into it. | N/A | 9 | 9:00
2019-02-05 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Disclosed axe filter is working on three screens. Amrit would also do it on the rest and make it sticky. | 110119 | 9 | 9:00
2019-02-06 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | tested the patch/fix for backfilling â€˜Axeâ€™ watchlist option at GoLive time. Now, just the changed config provided by Andrew to boot servers in a different way, needs to be tested. This doesnâ€™t affect the fix/patch already tested | 109935 | 9 | 9:00
2019-02-07 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | completed 4 screens with testing. In the 5th screen, there is some coding issue which I am looking into with him. In the remaining 2 screens, the requirement is not clear for which we have requested Chandan. | 110119 | 9 | 9:00
2019-01-07 | Amritpreet Singh | MKTX_Trading Platform Development | General | Integration & System Testing | Requirements Review/Analysis | Working on how to get the necessary permissions to a dealer so that they may send an inquiry or post an axe on a Muni bond. | N/A | 9 | 9:00
2019-02-08 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | took care of the coding issue he was facing in the 5th screen. We have requested a discussion with Chandan on Mon to clear our doubts on the three screens so that he may code for them and test them. | 110119 | 9 | 9:00
2019-01-08 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | After Chandan guided us towards permissions to dealer for trading/axing with Muni bonds, Amrit is now testing the Muni bonds axe filtering. Also, we have a code review with Andrew Gotte tomorrow. | N/A | 9 | 9:00
2019-01-09 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | Amrit successfully tested both disclosed and anonymous axe filtering on Muni bonds. Tomorrow, he would prepare a Db migration script for this requirement. As informed by Chandan, code review with Andrew Gotte would be on Mon. | N/A | 9 | 9:00
2019-01-10 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | trying to find out the flow in code/Db where the Watchlist filter preferences are stored. This is because on GoLive, those users who had earlier selected â€˜Axeâ€™ option should now see both â€˜Disclosed Axeâ€™ and â€˜Anonymous Axeâ€™ selected. He may need Andrewâ€™s guidance with this. | N/A | 9 | 9:00
2019-02-11 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | understood how to test the three screens, had lack of understanding in. started working on them. | 110119 | 9 | 9:00
2019-01-11 | Amritpreet Singh | MKTX_Trading Platform Development | General | Design | Design Documentation | Pending code review with Andrew Gotte and discussion on mapping old source (â€˜Axeâ€™) with both new sources (â€˜Anonymous Axeâ€™ and â€˜Disclosed Axeâ€™) automatically on GoLive. Did a small test today, code in current state is not doing that. | N/A | 9 | 9:00
2019-02-12 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | For 6th and 7th screen, got clarified the requirement with Hossam and would change the implementation accordingly | 110119 | 6 | 6:00
2019-02-12 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | tested the 5th screen today for this requirement | 110119 | 3 | 3:00
2019-02-13 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | debugging MKTX IG Active table (6th screen) data population to achieve the hold disclosed axe functionality. | 110119 | 9 | 9:00
2019-02-14 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | debugging MKTX IG Active table data population to achieve the hold disclosed axe functionality | 110119 | 9 | 9:00
2019-01-14 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Code Review | review done with chandan/amit | N/A | 2 | 2:00
2019-01-14 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework | code rework done | N/A | 2 | 2:00
2019-01-14 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | Ability to hold Disclosed Axe RTS Match Alertsâ€™ started to understand this requirement as his next assignment. | N/A | 5 | 5:00
2019-02-15 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | Meetings / Telecons / Query resolution (At Project Level) | helped nikita and neha with their tasks | - | 3 | 3:00
2019-02-15 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | debugging MKTX IG Active table data population to achieve the hold disclosed axe functionality. | 110119 | 6 | 6:00
2019-01-15 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Ability to hold Disclosed Axe RTS Match Alertsâ€™ started to understand this requirement as his next assignment. | N/A | 9 | 9:00
2019-01-16 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | â€“ â€˜Ability to hold Disclosed Axe RTS Match Alertsâ€™ doing server side changes for this requirement. | N/A | 9 | 9:00
2019-01-17 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | â€“ â€˜Ability to hold Disclosed Axe RTS Match Alertsâ€™ doing server side debugging for this requirement. | N/A | 9 | 9:00
2019-02-18 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | almost completed the 6th screen i.e. MKTX-IG Actives. would replicate similar logic in the last screen i.e. MKTX-IG New Issues | 110119 | 9 | 9:00
2019-01-18 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | â€“ â€˜Ability to hold Disclosed Axe RTS Match Alertsâ€™ doing server side debugging for this requirement. | N/A | 7 | 7:00
2019-01-18 | Amritpreet Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Trainings | KT to Nidhi and Nikita | N/A | 2 | 2:00
2019-02-19 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | finished the coding for all six screens. Would do thorough testing tomorrow | 110119 | 9 | 9:00
2019-02-20 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | testing the code changes he did for all the screens. | 110119 | 9 | 9:00
2019-02-21 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | 10.3 QA/Dev Walkthrough - Auto-close Trade Ticket | - | 1 | 1:00
2019-02-21 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | testing the code changes he did for all the screens. | 110119 | 8 | 8:00
2019-01-21 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | requested Chandan for RTS AXE xml. He is currently testing his filtering code for non axe, based upon what the user has selected | 108825 | 9 | 9:00
2019-02-22 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | testing the code changes he did for all the screens. | 110119 | 9 | 9:00
2019-01-22 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | got more insight from Chandan on this requirement. Would make code changes to meet current/improved understanding. | 108825 | 9 | 9:00
2019-01-23 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | As per the latest/correct understanding, Amrit made required code changes. He is now able to achieve the filtering for holding various RTS axe alerts. | 108825 | 7 | 7:00
2019-01-23 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing | in the process of exhaustive testing. | 108825 | 2 | 2:00
2019-01-24 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | Andrew Gotte has provided sample code/script for backfilling of â€˜Axeâ€™ option in watchlist at GoLive time. Now, would follow it and do the needful. | 109935 | 9 | 9:00
2019-01-25 | Amritpreet Singh | MKTX_Trading Platform Development | General | Other Project Activities | R&D | understood the approach needed to backfill â€˜Axeâ€™ watchlist option at GoLive time. He would now write the required code to achieve the same. | 109935 | 9 | 9:00
2019-01-28 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | coding the solution to backfill â€˜Axeâ€™ watchlist option at GoLive time. | 109935 | 9 | 9:00
2019-01-29 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | coding the solution to backfill â€˜Axeâ€™ watchlist option at GoLive time. | 109935 | 9 | 9:00
2019-01-30 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | coding the solution to backfill â€˜Axeâ€™ watchlist option at GoLive time. | 109935 | 9 | 9:00
2019-01-31 | Amritpreet Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding | tested the fix/patch for backfilling â€˜Axeâ€™ option in watchlist alerts at GoLive time. He would start with new requirement tomorrow. | 109935 | 9 | 9:00
2019-02-01 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Org Training attended | Lunch | N/A | 1 | 1:00
2019-02-01 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Org Training attended | Training done for Capital market | N/A | 3 | 3:00
2019-02-01 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Org Training attended | Training done for ISTQB | N/A | 1 | 1:00
2019-02-01 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | go through description ISTQB | N/A | 4 | 4:00
2019-02-04 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) | Training on financial markets | N/A | 1 | 1:00
2019-02-04 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | Lunch | N/A | 1 | 1:00
2019-02-04 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | study for financial markets | N/A | 7 | 7:00
2019-02-05 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) | Training on financial markets | N/A | 1 | 1:00
2019-02-05 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | Lunch | N/A | 1 | 1:00
2019-02-05 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | study for financial markets | N/A | 7 | 7:00
2019-02-06 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | Lunch | N/A | 1 | 1:00
2019-02-06 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | study for financial markets | N/A | 8 | 8:00
2019-02-07 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) | Training on financial markets | N/A | 1 | 1:00
2019-02-07 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | Lunch | N/A | 1 | 1:00
2019-02-07 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | study for financial markets | N/A | 7 | 7:00
2019-02-08 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) | Training on financial markets | N/A | 1 | 1:00
2019-02-08 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | Lunch | N/A | 1 | 1:00
2019-02-08 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | study for financial markets | N/A | 7 | 7:00
2019-02-11 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) | Training on financial markets | N/A | 1 | 1:00
2019-02-11 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | Lunch | N/A | 1 | 1:00
2019-02-11 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | study for financial markets | N/A | 7 | 7:00
2019-02-12 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) | Training on financial markets | N/A | 1 | 1:00
2019-02-12 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | Lunch | N/A | 1 | 1:00
2019-02-12 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | study for financial markets | N/A | 7 | 7:00
2019-02-13 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) | Training on financial markets | N/A | 2 | 2:00
2019-02-13 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | Lunch | N/A | 2 | 2:00
2019-02-13 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | study for financial markets | N/A | 14 | 14:00
2019-01-31 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Org Training attended | Lunch | N/A | 1 | 1:00
2019-01-31 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Org Training attended | Training done for ISTQB | N/A | 1 | 1:00
2019-01-31 | Anita Bisht | IRISES_IRIS-BSTS | General | Non Project | Self Study | go through description ISTQB | N/A | 7 | 7:00
2019-02-01 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-02-04 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 9 | 9:00
2019-02-05 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Interview |  |  | 9 | 9:00
2019-02-06 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-02-07 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-08 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-11 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-12 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-13 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-14 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-15 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-18 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-19 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-20 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 6 | 6:00
2019-02-20 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Org Training attended |  |  | 3 | 3:00
2019-02-21 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-01-21 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Org Training attended |  |  | 9 | 9:00
2019-02-22 | Arpita Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-01-22 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Org Training attended |  |  | 9 | 9:00
2019-01-23 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Org Training attended |  |  | 9 | 9:00
2019-01-24 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 9 | 9:00
2019-01-25 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-28 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 9 | 9:00
2019-01-29 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 9 | 9:00
2019-01-30 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 9 | 9:00
2019-01-31 | Arpita Singh | IRISES_IRIS-BSTS | General | Non Project | Interview |  |  | 9 | 9:00
2019-01-10 | Lakshya Mohan | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 9 | 9:00
2019-02-21 | Lakshya Mohan | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 9 | 9:00
2019-02-01 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Self study |  | 6 | 6:00
2019-02-01 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Environment setup-software download | N/A | 3 | 3:00
2019-02-04 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Code set up | N/A | 9 | 9:00
2019-02-05 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Code set up for another version | N/A | 9 | 9:00
2019-02-06 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | set up | N/A | 6 | 6:00
2019-02-06 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer | KT | N/A | 3 | 3:00
2019-02-07 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Self study and Hands on project code | N/A | 9 | 9:00
2019-02-08 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Self study and hands on project | N/A | 9 | 9:00
2019-01-10 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | On boarding work |  | 5 | 5:00
2019-01-10 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Self study |  | 4 | 4:00
2019-02-11 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Self study and hands on Project code | N/A | 9 | 9:00
2019-01-11 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 3 | 3:00
2019-01-11 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 6 | 6:00
2019-02-12 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Self study and hands on Project code | N/A | 9 | 9:00
2019-02-13 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Self study and hands on Project code | N/A | 9 | 9:00
2019-02-14 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Self study and hands on Project code | N/A | 9 | 9:00
2019-01-14 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | induction Training |  | 7 | 7:00
2019-01-14 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 2 | 2:00
2019-02-15 | Neha Venugopal | MKTX_Trading Platform Development | General | Development (CUT) | Environment Setup | Set up of 10.3.0 | CMS 110331 | 9 | 9:00
2019-01-15 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 1 | 1:00
2019-01-15 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | hands On Exercise |  | 8 | 8:00
2019-01-16 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 1 | 1:00
2019-01-16 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Client Interview preparation |  | 8 | 8:00
2019-01-17 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 1 | 1:00
2019-01-17 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Client Interview preparation |  | 8 | 8:00
2019-02-18 | Neha Venugopal | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Code analysis and trying to reproduce the issue | CMS 110331 | 9 | 9:00
2019-01-18 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 1 | 1:00
2019-01-18 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Hands on |  | 8 | 8:00
2019-02-19 | Neha Venugopal | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS 110331 | 9 | 9:00
2019-02-20 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer | Self study and hands on | N/A | 6 | 6:00
2019-02-20 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Org Training attended | FS Primer1 training |  | 3 | 3:00
2019-02-21 | Neha Venugopal | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS 110962 | 9 | 9:00
2019-01-21 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 3 | 3:00
2019-01-21 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 1 | 1:00
2019-01-21 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study |  | N/A | 5 | 5:00
2019-02-22 | Neha Venugopal | MKTX_Trading Platform Development | General | Development (CUT) | Code Review |  | CMS 110962 | 1 | 1:00
2019-02-22 | Neha Venugopal | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework |  | CMS 110962 | 3 | 3:00
2019-02-22 | Neha Venugopal | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS 110962 | 3 | 3:00
2019-02-22 | Neha Venugopal | MKTX_Trading Platform Development | General | Development (CUT) | Coding | Requirement analysis | CMS 108239 | 2 | 2:00
2019-01-22 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 2 | 2:00
2019-01-22 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 1 | 1:00
2019-01-22 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 6 | 6:00
2019-01-23 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 1 | 1:00
2019-01-23 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Self Study | N/A | 5 | 5:00
2019-01-23 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer | Self study and hands on of the project | N/A | 3 | 3:00
2019-01-24 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer | Self Study and hands on of the project | N/A | 3 | 3:00
2019-01-24 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 6 | 6:00
2019-01-25 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Self study | N/A | 7 | 7:00
2019-01-25 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer | hands on of the project | N/A | 2 | 2:00
2019-01-28 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer | hands on of the project | N/A | 3 | 3:00
2019-01-28 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Self study | N/A | 6 | 6:00
2019-01-29 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Self study | N/A | 6 | 6:00
2019-01-29 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer | Kt and handson on code | N/A | 3 | 3:00
2019-01-30 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Environment setup | N/A | 4 | 4:00
2019-01-30 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Self study |  | 5 | 5:00
2019-01-31 | Neha Venugopal | IRISES_IRIS-BSTS | General | Non Project | Self Study | Self study |  | 5 | 5:00
2019-01-31 | Neha Venugopal | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup | Environment setup | N/A | 4 | 4:00
2019-02-01 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 9 | 9:00
2019-01-02 | Nidhi Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup |  | N/A | 9 | 9:00
2019-01-03 | Nidhi Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Environment Setup |  | N/A | 9 | 9:00
2019-02-04 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 9 | 9:00
2019-01-04 | Nidhi Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-05 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 9 | 9:00
2019-02-06 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 9 | 9:00
2019-02-07 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 9 | 9:00
2019-01-07 | Nidhi Singh | MKTX_Trading Platform Development | General | Project Transition/KT | Knowledge Transfer |  | N/A | 9 | 9:00
2019-02-08 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 9 | 9:00
2019-01-08 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-01-09 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-01-10 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-02-11 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT-2 | 9 | 9:00
2019-01-11 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-02-12 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Meetings / Telecons / Query resolution |  | CMS-110766 | 9 | 9:00
2019-02-13 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110766 | 9 | 9:00
2019-02-14 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110766 | 9 | 9:00
2019-01-14 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-02-15 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT-6 | 9 | 9:00
2019-01-15 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-01-16 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-01-17 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | CMS-110595 | 9 | 9:00
2019-02-18 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-01-18 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-02-19 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110766 | 9 | 9:00
2019-02-20 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-02-21 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 8 | 8:00
2019-02-21 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110766 | 1 | 1:00
2019-01-21 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-02-22 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-01-22 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-01-23 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Code Review |  | CMS-110595 | 4 | 4:00
2019-01-23 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework |  | CMS-110595 | 5 | 5:00
2019-01-24 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | CMS-110595 | 9 | 9:00
2019-01-25 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | CMS-110595 | 9 | 9:00
2019-01-28 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | CMS-110595 | 9 | 9:00
2019-01-29 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 9 | 9:00
2019-01-30 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 9 | 9:00
2019-01-31 | Nidhi Singh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 9 | 9:00
2019-02-01 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Code Review |  | BREXIT | 1 | 1:00
2019-02-01 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework |  | BREXIT | 5 | 5:00
2019-02-01 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Meetings / Telecons / Query resolution |  | BREXIT | 1 | 1:00
2019-02-01 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 2 | 2:00
2019-02-01 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-02-04 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-02-04 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 5 | 5:00
2019-02-04 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 4 | 4:00
2019-02-05 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 10 | 10:00
2019-02-05 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 4 | 4:00
2019-02-05 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-02-06 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-02-06 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 3 | 3:00
2019-02-06 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 5 | 5:00
2019-02-07 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Code Review |  | BREXIT | 2 | 2:00
2019-02-07 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Environment Setup |  | BREXIT | 2 | 2:00
2019-02-07 | Nikita Arunabh | MKTX_Trading Platform Development | General | Project Transition/KT | KT Tasks |  | N/A | 4 | 4:00
2019-02-07 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-02-08 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-02-08 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Code Review |  | BREXIT | 2 | 2:00
2019-02-08 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework |  | BREXIT | 4 | 4:00
2019-02-08 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 2 | 2:00
2019-01-08 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-01-08 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 8 | 8:00
2019-01-09 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-01-09 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 8 | 8:00
2019-01-10 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-01-10 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 8 | 8:00
2019-02-11 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 9 | 9:00
2019-01-11 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-01-11 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 8 | 8:00
2019-02-12 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 3 | 3:00
2019-02-12 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 6 | 6:00
2019-02-13 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework |  | BREXIT | 6 | 6:00
2019-02-13 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 3 | 3:00
2019-02-14 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Test Case/Data Preparation |  | BREXIT | 2 | 2:00
2019-02-14 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | N/A | 7 | 7:00
2019-01-14 | Nikita Arunabh | MKTX_Trading Platform Development | General | Other Project Activities | Project Trainings |  | N/A | 9 | 9:00
2019-01-14 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-02-15 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 4 | 4:00
2019-02-15 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 5 | 5:00
2019-01-15 | Nikita Arunabh | MKTX_Trading Platform Development | General | Other Project Activities | Project Trainings |  | N/A | 9 | 9:00
2019-01-16 | Nikita Arunabh | MKTX_Trading Platform Development | General | Project Transition/KT | Trainings |  | N/A | 9 | 9:00
2019-01-17 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Environment Setup |  | N/A | 9 | 9:00
2019-02-18 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Code Review |  | BREXIT | 2 | 2:00
2019-02-18 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 5 | 5:00
2019-02-18 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 2 | 2:00
2019-01-18 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Environment Setup |  | N/A | 9 | 9:00
2019-02-19 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework |  | BREXIT | 2 | 2:00
2019-02-19 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 7 | 7:00
2019-02-20 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Code Rework |  | BREXIT | 3 | 3:00
2019-02-20 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 6 | 6:00
2019-02-21 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Coding |  | BREXIT | 2 | 2:00
2019-02-21 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 7 | 7:00
2019-01-21 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Environment Setup |  | N/A | 9 | 9:00
2019-02-22 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Unit Testing |  | BREXIT | 9 | 9:00
2019-01-22 | Nikita Arunabh | MKTX_Trading Platform Development | General | Other Project Activities | Environment Setup |  | N/A | 9 | 9:00
2019-01-23 | Nikita Arunabh | MKTX_Trading Platform Development | General | Other Project Activities | Environment Setup |  | N/A | 9 | 9:00
2019-01-24 | Nikita Arunabh | MKTX_Trading Platform Development | General | Other Project Activities | Environment Setup |  | N/A | 9 | 9:00
2019-01-25 | Nikita Arunabh | MKTX_Trading Platform Development | General | Other Project Activities | Environment Setup |  | N/A | 9 | 9:00
2019-01-28 | Nikita Arunabh | MKTX_Trading Platform Development | General | Other Project Activities | Environment Setup |  | N/A | 8 | 8:00
2019-01-28 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-01-29 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-01-29 | Nikita Arunabh | MKTX_Trading Platform Development | General | Other Project Activities | Environment Setup |  | N/A | 8 | 8:00
2019-01-30 | Nikita Arunabh | MKTX_Trading Platform Development | General | Other Project Activities | Environment Setup |  | BREXIT | 8 | 8:00
2019-01-30 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-01-31 | Nikita Arunabh | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | lunch |  | 1 | 1:00
2019-01-31 | Nikita Arunabh | MKTX_Trading Platform Development | General | Development (CUT) | Environment Setup |  | N/A | 8 | 8:00
2019-02-01 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-02-05 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 4.5 | 4:30
2019-02-06 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 4.5 | 4:30
2019-02-07 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 4.5 | 4:30
2019-02-08 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 4.5 | 4:30
2019-02-11 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 4.5 | 4:30
2019-02-12 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 9 | 9:00
2019-02-13 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 9 | 9:00
2019-02-14 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 9 | 9:00
2019-02-15 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 9 | 9:00
2019-01-17 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-02-18 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 9 | 9:00
2019-01-18 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-02-19 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 9 | 9:00
2019-02-20 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 9 | 9:00
2019-01-21 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-22 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-23 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-24 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-25 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-28 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-29 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-30 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-31 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Idle Time (Bench Time) |  |  | 9 | 9:00
2019-01-31 | Rahul Rajput | IRISES_IRIS-BSTS | General | Non Project | Leave | On leave - Auto Entry |  | 4.5 | 4:30
2019-02-04 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Interview | Interviews taken for PLSQL (In Memory DB) requirement | NA | 2 | 2:00
2019-02-05 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Leave | half day leave | NA | 4.5 | 4:30
2019-02-06 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Interview | Interviewed candidate for PLSQL/MemSQL requirement | NA | 2 | 2:00
2019-02-07 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Interview | Interviews | NA | 2 | 2:00
2019-02-08 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Interview | Interviews | NA | 4 | 4:00
2019-02-11 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Interview |  | NA | 1.5 | 1:30
2019-02-11 | Rikki Bindra | MKTX_Trading Platform Development | General | Project Management | Data Collation & Analysis | MWB Data collation | NA | 2.25 | 2:15
2019-02-12 | Rikki Bindra | MKTX_Trading Platform Development | General | Project Management | Monitoring & Reporting |  | NA | 2.25 | 2:15
2019-02-13 | Rikki Bindra | MKTX_Trading Platform Development | General | Project Management | Monitoring & Reporting |  | NA | 4.5 | 4:30
2019-02-14 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Leave |  | NA | 9 | 9:00
2019-02-15 | Rikki Bindra | MKTX_Trading Platform Development | General | Project Management | Monitoring & Reporting |  | NA | 2.5 | 2:30
2019-02-18 | Rikki Bindra | MKTX_Trading Platform Development | General | Project Management | Monitoring & Reporting |  | NA | 2.5 | 2:30
2019-02-18 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) |  | NA | 4 | 4:00
2019-02-19 | Rikki Bindra | MKTX_Trading Platform Development | General | Project Management | Monitoring & Reporting |  | NA | 2.5 | 2:30
2019-02-20 | Rikki Bindra | MKTX_Trading Platform Development | General | Project Management | Monitoring & Reporting |  | NA | 2.5 | 2:30
2019-02-21 | Rikki Bindra | MKTX_Trading Platform Development | General | Project Management | Monitoring & Reporting |  | NA | 2.5 | 2:30
2019-02-21 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous |  |  | 4 | 4:00
2019-02-22 | Rikki Bindra | MKTX_Trading Platform Development | General | Project Management | Data Collation & Analysis |  | NA | 2.5 | 2:30
2019-01-28 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) | MA - Session/walkthrough/meetings etc on PM activities | NA | 9 | 9:00
2019-01-29 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Meetings (Non Project) | MA - Session/walkthrough/meetings etc on PM activities | NA | 9 | 9:00
2019-01-30 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | MA - Session/walkthrough/meetings etc on PM activities | NA | 9 | 0.375
2019-01-31 | Rikki Bindra | IRISES_IRIS-BSTS | General | Non Project | Miscellaneous | MA - Session/walkthrough/meetings etc on PM activities | NA | 9 | 0.375
2019-02-14 | Satyarth Tewari | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 9 | 0.375
2019-02-15 | Satyarth Tewari | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 9 | 0.375
2019-02-18 | Satyarth Tewari | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 9 | 0.375
2019-02-19 | Satyarth Tewari | IRISES_IRIS-BSTS | General | Non Project | Self Study |  |  | 9 | 0.375
2019-02-20 | Satyarth Tewari | MKTX_Trading Platform Development | General | Other Project Activities | Idle Time |  | NA | 8.5 | 0.35417
2019-02-20 | Satyarth Tewari | MKTX_Trading Platform Development | General | Other Project Activities | Meetings / Telecons / Query resolution (At Project Level) | KT from Amit. | NA | 0.5 | 0.020833
2019-02-21 | Satyarth Tewari | MKTX_Trading Platform Development | General | Other Project Activities | Idle Time |  | NA | 8.5 | 0.35417
2019-02-21 | Satyarth Tewari | MKTX_Trading Platform Development | General | Other Project Activities | Idle Time | KT from Amit. | NA | 0.5 | 0.020833
2019-02-22 | Satyarth Tewari | MKTX_Trading Platform Development | General | Other Project Activities | Idle Time |  | NA | 8.5 | 0.35417
2019-02-22 | Satyarth Tewari | MKTX_Trading Platform Development | General | Other Project Activities | Idle Time | KT from Amit. | NA | 0.5 | 0.020833

## Ticket Status
Ticket ID | Status
CMS-108825 | In Progress
CMS-109935 | Resolved
CMS-110119 | In Progress
BREXIT | Resolved
BREXIT-1 | Resolved
BREXIT-2 | Resolved
BREXIT-3 | Resolved
BREXIT-5 | Resolved
BREXIT-6 | Resolved
CMS-111110 | In Progress
CMS-110962 | Resolved
CMS-108239 | Resolved
CMS-110331 | Resolved
CMS-110766 | Resolved
CMS-110595 | In Progress

## Miscellaneous
Trading Platform CM Audit Owners

## Dashboard
Project Support | 0
QA Support | 0
Rework | 0
BAU Tasks | 0
Backlog | 0
Leaves | 0
Non Project Activities | 0
Project Management | 0
Company Holiday | 0
Total Effort | 0
Effort Towards JIRA Tickets | 0