## Analysis
TTS Ticket ID | Errors | Requirement / Impact Analysis | Design | Code | Code Review | UT | UT Review | QA Support | Rework | Leaves | Company Holiday | Non Project | Project Management | Project BAU | Project Support | Start Date | End Date | Status | Type | Owner
N/A | [Status not found] | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 13 | 2019-01-02 | 2019-02-22 |  | SUPPORT | Arpita Singh
CMS 110962 | [Status not found] | 0 | 0 | 12 | 1 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-22 |  |  | Neha Venugopal
108825.0 | [Status not found] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-21 | 2019-02-04 |  |  | Amritpreet Singh
CMS 110331 | [Status not found] | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 2019-02-15 | 2019-02-19 |  |  | Neha Venugopal
CMS 108239 | [Status not found] | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-22 | 2019-02-22 |  |  | Neha Venugopal
CMS-110766 |  | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 2019-02-12 | 2019-02-21 | Resolved | ENHANCEMENT | Nidhi Singh
109935.0 | [Status not found] | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-02 | 2019-02-06 |  |  | Amritpreet Singh
BREXIT |  | 0 | 0 | 104 | 7 | 85 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 10 | 1 | 2019-01-21 | 2019-02-22 | Resolved | ENHANCEMENT | Nikita Arunabh
CMS-110595 |  | 0 | 0 | 35 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-08 | 2019-02-22 | In Progress | BACKLOG | Nidhi Singh
- | [Status not found] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2019-02-15 | 2019-02-21 |  | SUPPORT | Amritpreet Singh
(blank) | [Status not found] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 2019-01-08 | 2019-02-21 |  | SUPPORT | Lakshya Mohan
111110.0 | [Status not found] | 0 | 0 | 4.5 | 2 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-22 |  |  | Amit Khera
BREXIT-3 |  | 3 | 0 | 11 | 6 | 14 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-07 | Resolved | ENHANCEMENT | Amit Khera
BREXIT-6 |  | 4.5 | 0 | 13.5 | 6.5 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-14 | 2019-02-18 | Resolved | ENHANCEMENT | Amit Khera
BREXIT-5 |  | 9 | 0 | 13.5 | 2 | 4.5 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-13 | Resolved | ENHANCEMENT | Amit Khera
NA | [Status not found] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.5 | 0 | 51.5 | 24 | 0 | 0 | 2019-01-28 | 2019-02-22 |  | SUPPORT | Rikki Bindra
BREXIT-2 |  | 0 | 0 | 0 | 2 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-11 | Resolved | ENHANCEMENT | Nidhi Singh
110119.0 | [Status not found] | 24 | 0 | 73 | 1 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-22 |  |  | Amritpreet Singh
BREXIT-1 |  | 6 | 0 | 6 | 6 | 9 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-25 | 2019-02-20 | Resolved | ENHANCEMENT | Amit Khera
BREXIT-8 | [Status not found] | 0 | 0 | 3 | 1 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 |  |  | Amit Khera