## Analysis
TTS Ticket ID | Errors | Requirement / Impact Analysis | Design | Code | Code Review | UT | UT Review | QA Support | Rework | Leaves | Company Holiday | Non Project | Project Management | Project BAU | Project Support | Start Date | End Date | Status | Type | Owner | Converted Ticket ID
PPB-2650 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Open | WIP | Anju Gupta
PPB-2530 |  | 5 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-22 | Open | WIP | Abhishek Jain
PPB-2376 |  | 11 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2019-01-30 | 2019-02-06 | Open | WIP | Anurag Ajmera
PPB-2653 |  | 6 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-21 | Open | WIP | Anju Gupta
PPB-2416 |  | 9 | 0 | 36 | 9.17 | 9 | 9.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-02-08 | Resolved | ENHANCEMENT | Priyatosh Kashyap
SFTR-561 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-25 | 2019-01-28 | Closed | DEFECT | Vinod Kumar
QREL-1440 | [Not all phases charged in TTS] | 1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-11 | Resolved | ENHANCEMENT | Alok Tripathi
SFTR-564 | [Not all phases charged in TTS] | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-22 | 2019-01-31 | Resolved | ENHANCEMENT | Ashish Pandey
PPB-2415 | [Not all phases charged in TTS] | 3 | 0 | 35 | 9 | 15.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2019-01-29 | 2019-02-08 | Resolved | ENHANCEMENT | Priyatosh Kashyap
QREL-1441 | [Not all phases charged in TTS] | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2019-02-04 | 2019-02-06 | Closed | ENHANCEMENT | Unis Ahmad Beig
SFTR-563 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-07 | Resolved | DEFECT | Rahul Uniyal
QREL-1285 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-05 | 2019-01-31 | Open | BACKLOG | Abhishek Jain
SFTR-569 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-29 | Closed | DEFECT | Vinod Kumar
QREL-1449 | [Not all phases charged in TTS] | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2019-02-04 | 2019-02-06 | Closed | ENHANCEMENT | Unis Ahmad Beig
SFTR-329 | [Not all phases charged in TTS] | 0 | 0 | 20 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-16 | 2019-02-14 | Resolved | ENHANCEMENT | Vinod Kumar
QREL-1446 | [Not all phases charged in TTS] | 2 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-11 | Resolved | ENHANCEMENT | Anju Gupta
SFTR-566 |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-06 | Closed | ANALYSIS | Arjun Singh
SFTR-565 | [Not all phases charged in TTS] | 0 | 0 | 8 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-24 | 2019-02-01 | Resolved | ENHANCEMENT | Ajay Chhillar
QREL-1444 | [Not all phases charged in TTS] | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-05 | 2019-02-05 | Closed | ENHANCEMENT | Anju Gupta
SFTR-568 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-29 | Closed | DEFECT | Arjun Singh
QREL-1445 | [Not all phases charged in TTS] | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-06 | Closed | ENHANCEMENT | Anju Gupta
SFTR-567 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-29 | Closed | DEFECT | Vinod Kumar
(blank) | [Status not found] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 11 | 0 | 0 | 0 | 2018-11-29 | 2019-02-22 |  | SUPPORT | Ashish Pandey
PPB-2422 | [Not all phases charged in TTS] | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-20 | Resolved | ENHANCEMENT | Abhishek Jain
QREL-1453 | [Not all phases charged in TTS] | 2 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-05 | 2019-02-07 | Closed | ENHANCEMENT | Anju Gupta
PPB-2548 |  | 10 | 0 | 17 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-22 | In Progress | WIP | Priyatosh Kashyap
SFTR-551 | [Not all phases charged in TTS] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-12 | 2019-02-14 | Resolved | ENHANCEMENT | Rahul Uniyal
QREL-1451 | [Not all phases charged in TTS] | 7 | 0 | 18 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-13 | Closed | ENHANCEMENT | Ashish Pandey
SFTR-311 |  | 8 | 0 | 23 | 0.75 | 4 | 0.25 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-20 | Resolved | ENHANCEMENT | Ajay Chhillar
SFTR-553 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-01-31 | Closed | DEFECT | Rahul Uniyal
SFTR-399 | [Not all phases charged in TTS] | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-07 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
QREL-1452 | [Not all phases charged in TTS] | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-07 | Closed | ENHANCEMENT | Anju Gupta
SFTR-552 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-06 | Closed | ANALYSIS | Arjun Singh
SFTR-398 | [Not all phases charged in TTS] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-18 | 2019-01-28 | Resolved | ENHANCEMENT | Vinod Kumar
SFTR-394 |  | 47 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-22 | Open | WIP | Peer Hasan Ansari
QREL-1458 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 | Closed | DEFECT | Anurag Ajmera
SFTR-554 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-23 | 2019-02-01 | Closed | DEFECT | Rahul Uniyal
TIP-108 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-23 | 2019-01-28 | Open | BACKLOG | Abhishek Jain
QREL-1455 | [Not all phases charged in TTS] | 4 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-08 | Closed | ENHANCEMENT | Rohit Singh
QREL-1456 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-04 | Reopened | WIP | Anurag Ajmera
SFTR-556 | [Not all phases charged in TTS] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-02-06 | Resolved | ENHANCEMENT | Vinod Kumar
E2-356 | [Not all phases charged in TTS] | 9 | 0 | 14 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-06 | Resolved | ENHANCEMENT | Abhishek Jain
QREL-1509 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 | Closed | DEFECT | Anurag Ajmera
QREL-1507 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Closed | ANALYSIS | Anju Gupta
E2-355 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-01-31 | Closed | ANALYSIS | Unis Ahmad Beig
PPB-2311 | [Not all phases charged in TTS] | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-02-07 | Closed | ENHANCEMENT | Abhishek Jain
SFTR-386 | [Not all phases charged in TTS] | 0 | 0 | 0 | 4 | 7 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-14 | 2019-02-01 | Resolved | ENHANCEMENT | Ajay Chhillar
INQ-837 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-24 | 2019-02-08 | Open | BACKLOG | Anurag Ajmera | PPB-2657
QREL-1465 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Anju Gupta
INQ-715 |  | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-03 | 2019-02-01 | Open | BACKLOG | Peer Hasan Ansari | PPB-2638
SFTR-388 |  | 13 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-14 | In Progress | WIP | Arjun Singh
SFTR-387 |  | 17 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-22 | Open | WIP | Vinod Kumar
QREL-1340 |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-08 | 2019-02-06 | Open | BACKLOG | Unis Ahmad Beig | PPB-2642
INQ-717 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-07 | Closed | ANALYSIS | Rohit Singh
SFTR-548 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-21 | 2019-02-13 | Closed | ANALYSIS | Arjun Singh
INQ-950 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-11 | Open | WIP | Robina Dhingra | PPB-2659
INQ-675 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-11-29 | 2019-02-15 | In Progress | BACKLOG | Rohit Singh
QREL-1506 | [Not all phases charged in TTS] | 2 | 0 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 | Resolved | ENHANCEMENT | Unis Ahmad Beig
E2-350 | [Not all phases charged in TTS] | 0 | 0 | 9 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-17 | 2019-02-08 | Closed | ENHANCEMENT | Unis Ahmad Beig
QREL-1501 | [Not all phases charged in TTS] | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-15 | Resolved | ENHANCEMENT | Alok Tripathi
QREL-1468 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Anju Gupta
QREL-1502 | [Not all phases charged in TTS] | 3 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-15 | Resolved | ENHANCEMENT | Anju Gupta
INQ-953 |  | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-13 | Closed | ANALYSIS | Priyatosh Kashyap
SFTR-543 | [Not all phases charged in TTS] | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-24 | 2019-02-06 | Resolved | ENHANCEMENT | Rahul Uniyal
QREL-1467 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-07 | Closed | ANALYSIS | Abhishek Jain
QREL-1500 |  | 5 | 0 | 9 | 1.25 | 4 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-18 | 2019-02-21 | Resolved | ENHANCEMENT | Anju Gupta
TIP-118 | [Not all phases charged in TTS] | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-24 | 2019-01-29 | Resolved | ENHANCEMENT | Anju Gupta
SFTR-408 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-17 | 2019-01-29 | Resolved | ANALYSIS | Arjun Singh
QREL-1473 | [Not all phases charged in TTS] | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-06 | Resolved | ENHANCEMENT | Anju Gupta
SFTR-410 |  | 5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-12 | Open | WIP | Arjun Singh
QREL-1474 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-11 | Resolved | ANALYSIS | Anju Gupta
SFTR-376 |  | 0 | 0 | 13 | 2 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-13 | Open | WIP | Vinod Kumar
QREL-1471 | [Not all phases charged in TTS] | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-12 | Closed | ENHANCEMENT | Anju Gupta
SFTR-373 | [Not all phases charged in TTS] | 0 | 0 | 1 | 0.75 | 0 | 0.25 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-14 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
PPB-2605 | [Not all phases charged in TTS] | 3 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-15 | 2019-01-30 | Resolved | ENHANCEMENT | Rohit Singh
QREL-1470 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Anju Gupta
INQ-961 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Closed | ANALYSIS | Anurag Ajmera
E2-360 | [Not all phases charged in TTS] | 4 | 0 | 10 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-12 | Resolved | ENHANCEMENT | Unis Ahmad Beig
QREL-1479 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Anju Gupta
QREL-1477 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Abhishek Jain
QREL-1511 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Closed | ANALYSIS | Priyatosh Kashyap
PPB-2573 |  | 2 | 0 | 2.5 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-24 | 2019-02-06 | Resolved | ENHANCEMENT | Peer Hasan Ansari
QREL-1490 | [Not all phases charged in TTS] | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Resolved | ENHANCEMENT | Ashish Pandey
PPB-2577 |  | 15 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-18 | Open | WIP | Anju Gupta
PPB-2576 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Resolved | ANALYSIS | Abhishek Jain
INQ-934 |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-02-01 | Closed | ANALYSIS | Abhishek Jain
QREL-1484 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Abhishek Jain
INQ-933 |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-01 | In Progress | WIP | Priyatosh Kashyap
QREL-1361 |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-14 | 2019-02-04 | In Progress | BACKLOG | Rohit Singh
QREL-934 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-01 | Closed | ANALYSIS | Abhishek Jain
INQ-939 |  | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-14 | Resolved | ANALYSIS | Priyatosh Kashyap
PPB-2616 | [Not all phases charged in TTS] | 4 | 0 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2019-01-31 | 2019-02-18 | Resolved | ENHANCEMENT | Anurag Ajmera
SFTR-482 |  | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 2019-01-25 | 2019-02-22 | Open | BACKLOG | Alok Tripathi
QREL-1407 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-28 | Open | WIP | Anurag Ajmera
QREL-1525 | [Not all phases charged in TTS] | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-22 | 2019-02-22 | Resolved | ENHANCEMENT | Arjun Singh
SFTR-522 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-18 | 2019-01-31 | Closed | DEFECT | Vinod Kumar
INQ-898 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-23 | 2019-01-29 | In Progress | BACKLOG | Abhishek Jain
QREL-1488 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Open | WIP | Anju Gupta
QREL-1489 | [Not all phases charged in TTS] | 6 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-12 | 2019-02-13 | Resolved | ENHANCEMENT | Unis Ahmad Beig
SFTR-402 | [Not all phases charged in TTS] | 4 | 0 | 7 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-02-01 | Resolved | ENHANCEMENT | Arjun Singh
QREL-1368 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-23 | 2019-01-29 | Closed | DEFECT | Ashish Pandey
SFTR-629 |  | 4 | 0 | 12 | 0.75 | 4 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-22 | Resolved | ENHANCEMENT | Ajay Chhillar
QREL-1419 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-25 | 2019-01-28 | Closed | ANALYSIS | Anurag Ajmera
PPB-2584 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-30 | In Progress | WIP | Anju Gupta
PPB-2622 | [Not all phases charged in TTS] | 0 | 0 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-18 | Resolved | ENHANCEMENT | Abhishek Jain
PPB-2586 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-13 | In Progress | WIP | Rohit Singh
PPB-2625 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-28 | Open | WIP | Anju Gupta
QREL-1495 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-22 | 2019-02-22 | Open | WIP | Abhishek Jain
SFTR-630 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Resolved | ANALYSIS | Vinod Kumar
PPB-2503 | [Not all phases charged in TTS] | 24 | 0 | 9 | 6 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2019-02-05 | 2019-02-20 | Resolved | ENHANCEMENT | Abhishek Jain
NA | [Status not found] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.5 | 0 | 51.5 | 45.5 | 0 | 20.5 | 2018-11-26 | 2019-02-22 |  | SUPPORT | Anurag Ajmera
QREL-1372 | [Not all phases charged in TTS] | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Resolved | ENHANCEMENT | Ashish Pandey
PPB-2509 | [Not all phases charged in TTS] | 10 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-14 | 2019-02-22 | Resolved | ENHANCEMENT | Kavita Bais
QREL-429 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-11-28 | 2019-02-20 | Open | BAU | Priyatosh Kashyap
PPB-2506 |  | 27 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-12 | 2019-02-22 | Open | WIP | Robina Dhingra
PPB-2507 | [Not all phases charged in TTS] | 0 | 0 | 9 | 1.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-21 | 2019-02-04 | Resolved | ENHANCEMENT | Rohit Singh
PPB--2616 | [Status not found] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-01-30 |  |  | Anju Gupta
INQ-942 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-08 | In Progress | WIP | Abhishek Jain
QREL-1411 | [Not all phases charged in TTS] | 6 | 0 | 11 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-25 | 2019-02-14 | Closed | ENHANCEMENT | Priyatosh Kashyap
SFTR-479 | [Not all phases charged in TTS] | 2 | 0 | 16 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-02-01 | Resolved | ENHANCEMENT | Arjun Singh
N/A | [Status not found] | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 27 | 0 | 0 | 0 | 0 | 19 | 2018-11-26 | 2019-02-22 |  | SUPPORT | Kavita Bais
SFTR-618 | [Not all phases charged in TTS] | 3 | 0 | 0 | 0.75 | 9 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-21 | Resolved | ENHANCEMENT | Vinod Kumar
QREL-1391 | [Not all phases charged in TTS] | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-01-30 | Resolved | ENHANCEMENT | Unis Ahmad Beig
PPB-2633 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-04 | Open | WIP | Abhishek Jain
PPB-2234 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 | In Progress | WIP | Abhishek Jain
PPB-2510 | [Not all phases charged in TTS] | 16 | 0 | 101 | 0 | 18 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-24 | 2019-02-19 | Resolved | ENHANCEMENT | Kavita Bais
INQ-913 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-29 | Open | WIP | Priyatosh Kashyap
SFTR-341 | [Not all phases charged in TTS] | 0 | 0 | 11 | 1 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-22 | 2019-01-31 | Resolved | ENHANCEMENT | Peer Hasan Ansari
QREL-1385 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-29 | Closed | ANALYSIS | Anurag Ajmera
SFTR-586 | [Not all phases charged in TTS] | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
SFTR-585 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-01-31 | Closed | DEFECT | Rahul Uniyal
PPB-2517 | [Not all phases charged in TTS] | 4 | 0 | 68 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-18 | Resolved | ENHANCEMENT | Abhishek Jain
PPB-2638 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-06 | Open | WIP | Peer Hasan Ansari
SFTR-582 | [Not all phases charged in TTS] | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-20 | Resolved | ENHANCEMENT | Vinod Kumar
QREL-1382 | [Not all phases charged in TTS] | 5 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-29 | Closed | ENHANCEMENT | Anju Gupta
SFTR-460 | [Not all phases charged in TTS] | 0 | 0 | 5 | 0.75 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-21 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
BAU-2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 2018-12-10 | 2019-02-22 | Open | BAU | Ajay Chhillar
BAU-3 |  | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 2018-11-26 | 2019-02-19 | Reopened | SUPPORT | Arjun Singh
INQ-910 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-28 | Resolved | ANALYSIS | Rohit Singh
QREL-1425 | [Not all phases charged in TTS] | 23 | 0 | 6 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-02-11 | Resolved | ENHANCEMENT | Rohit Singh
BAU-5 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-07 | Open | SUPPORT | Priyatosh Kashyap
SFTR-622 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-15 | Open | WIP | Rahul Uniyal
SFTR-607 |  | 9 | 0 | 12 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-12 | In Progress | WIP | Peer Hasan Ansari
SFTR-606 | [Not all phases charged in TTS] | 0 | 0 | 0 | 0.75 | 0 | 0.25 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
SFTR-608 |  | 13 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-12 | 2019-02-22 | Open | WIP | Rahul Uniyal
PPB-2643 | [Not all phases charged in TTS] | 2 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-22 | Resolved | ENHANCEMENT | Abhishek Jain
PPB-2642 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-13 | Open | WIP | Unis Ahmad Beig
QREL-1431 |  | 14 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-05 | 2019-02-18 | Open | WIP | Ashish Pandey
SFTR-330 |  | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-13 | In Progress | WIP | Ajay Chhillar
QREL-1432 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-01-30 | Closed | ANALYSIS | Anurag Ajmera
SFTR-575 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-28 | Closed | DEFECT | Vinod Kumar
QREL-1430 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-29 | Resolved | ANALYSIS | Abhishek Jain
PPB-2646 | [Not all phases charged in TTS] | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Resolved | ENHANCEMENT | Arjun Singh
QREL-1394 | [Not all phases charged in TTS] | 0 | 0 | 14 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-25 | 2019-02-15 | Closed | ENHANCEMENT | Unis Ahmad Beig
INQ-928 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-01-31 | Open | WIP | Anju Gupta | PPB-2632
PPB-2529 | [Not all phases charged in TTS] | 0 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-09 | 2019-01-29 | Resolved | ENHANCEMENT | Rohit Singh
QREL-1439 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-02-05 | Resolved | DEFECT | Ashish Pandey
SFTR-613 | [Not all phases charged in TTS] | 0 | 0 | 6 | 2.75 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-14 | Resolved | ENHANCEMENT | Arjun Singh
QREL-1437 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-04 | Open | WIP | Anurag Ajmera
QREL-1438 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-29 | Closed | ANALYSIS | Anurag Ajmera
SFTR-615 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-14 | 2019-02-14 | Closed | ANALYSIS | Arjun Singh
SFTR-610 |  | 9 | 0 | 14 | 0.75 | 4 | 0.25 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-20 | Resolved | ENHANCEMENT | Ajay Chhillar
SFTR-335 | [Not all phases charged in TTS] | 0 | 0 | 12 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-21 | 2019-01-30 | Resolved | ENHANCEMENT | Peer Hasan Ansari
SFTR-576 | [Not all phases charged in TTS] | 2 | 0 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-30 | Resolved | ENHANCEMENT | Ajay Chhillar
QREL-1436 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-01-30 | Closed | ANALYSIS | Anurag Ajmera
INQ-920 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | In Progress | WIP | Rohit Singh
SFTR-612 | [Not all phases charged in TTS] | 0 | 0 | 9 | 0.75 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-12 | Resolved | ENHANCEMENT | Vinod Kumar
INQ-886 | [Not all phases charged in TTS] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2019-01-22 | 2019-02-14 | Closed | ENHANCEMENT | Rohit Singh
SFTR-579 |  | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-18 | 2019-02-21 | Open | WIP | Vinod Kumar
QREL-1434 | [Not all phases charged in TTS] | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-05 | Closed | ENHANCEMENT | Peer Hasan Ansari
SFTR-611 |  | 6 | 0 | 12 | 0.75 | 8 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-14 | 2019-02-19 | Resolved | ENHANCEMENT | Ajay Chhillar