## Analysis
TTS Ticket ID | Errors | Requirement / Impact Analysis | Design | Code | Code Review | UT | UT Review | QA Support | Rework | Leaves | Company Holiday | Non Project | Project Management | Project BAU | Project Support | Start Date | End Date | Status | Type | Owner
PPB-2650 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Open | WIP | Anju Gupta
PPB-2530 |  | 5 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-22 | Open | WIP | Abhishek Jain
PPB-2376 |  | 11 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2019-01-30 | 2019-02-06 | Open | WIP | Anurag Ajmera
PPB-2653 |  | 6 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-21 | Open | WIP | Anju Gupta
PPB-2416 |  | 9 | 0 | 36 | 9.17 | 9 | 9.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-02-08 | Resolved | ENHANCEMENT | Priyatosh Kashyap
SFTR-561 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-25 | 2019-01-28 | Closed | DEFECT | Vinod Kumar
QREL-1440 | Not all phases charged in TTS | 1 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-11 | Resolved | ENHANCEMENT | Alok Tripathi
SFTR-564 | Not all phases charged in TTS | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-22 | 2019-01-31 | Resolved | ENHANCEMENT | Ashish Pandey
PPB-2415 | Not all phases charged in TTS | 3 | 0 | 35 | 9 | 15.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2019-01-29 | 2019-02-08 | Resolved | ENHANCEMENT | Priyatosh Kashyap
QREL-1441 | Not all phases charged in TTS | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2019-02-04 | 2019-02-06 | Closed | ENHANCEMENT | Unis Ahmad Beig
SFTR-563 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-07 | Resolved | DEFECT | Rahul Uniyal
QREL-1285 | Opened since december. Reason? | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-05 | 2019-01-31 | Open | BACKLOG | Abhishek Jain
SFTR-569 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-29 | Closed | DEFECT | Vinod Kumar
QREL-1449 | Not all phases charged in TTS | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2019-02-04 | 2019-02-06 | Closed | ENHANCEMENT | Unis Ahmad Beig
SFTR-329 | Not all phases charged in TTS | 0 | 0 | 20 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-16 | 2019-02-14 | Resolved | ENHANCEMENT | Vinod Kumar
QREL-1446 | Not all phases charged in TTS | 2 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-11 | Resolved | ENHANCEMENT | Anju Gupta
SFTR-566 |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-06 | Closed | ANALYSIS | Arjun Singh
SFTR-565 | Not all phases charged in TTS | 0 | 0 | 8 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-24 | 2019-02-01 | Resolved | ENHANCEMENT | Ajay Chhillar
QREL-1444 | Not all phases charged in TTS | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-05 | 2019-02-05 | Closed | ENHANCEMENT | Anju Gupta
SFTR-568 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-29 | Closed | DEFECT | Arjun Singh
QREL-1445 | Not all phases charged in TTS | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-06 | Closed | ENHANCEMENT | Anju Gupta
SFTR-567 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-29 | Closed | DEFECT | Vinod Kumar
PPB-2422 | Not all phases charged in TTS | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-20 | Resolved | ENHANCEMENT | Abhishek Jain
QREL-1453 | Not all phases charged in TTS | 2 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-05 | 2019-02-07 | Closed | ENHANCEMENT | Anju Gupta
PPB-2548 |  | 10 | 0 | 17 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-22 | In Progress | WIP | Priyatosh Kashyap
SFTR-551 | Not all phases charged in TTS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-12 | 2019-02-14 | Resolved | ENHANCEMENT | Rahul Uniyal
QREL-1451 | Not all phases charged in TTS | 7 | 0 | 18 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-13 | Closed | ENHANCEMENT | Ashish Pandey
SFTR-311 |  | 8 | 0 | 23 | 0.75 | 4 | 0.25 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-20 | Resolved | ENHANCEMENT | Ajay Chhillar
SFTR-553 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-01-31 | Closed | DEFECT | Rahul Uniyal
SFTR-399 | Not all phases charged in TTS | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-07 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
QREL-1452 | Not all phases charged in TTS | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-07 | Closed | ENHANCEMENT | Anju Gupta
SFTR-552 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-06 | Closed | ANALYSIS | Arjun Singh
SFTR-398 | Not all phases charged in TTS | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-18 | 2019-01-28 | Resolved | ENHANCEMENT | Vinod Kumar
SFTR-394 |  | 47 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-22 | Open | WIP | Peer Hasan Ansari
QREL-1458 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 | Closed | DEFECT | Anurag Ajmera
SFTR-554 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-23 | 2019-02-01 | Closed | DEFECT | Rahul Uniyal
TIP-108 |  | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-23 | 2019-01-28 | Open | BACKLOG | Abhishek Jain
QREL-1455 | Not all phases charged in TTS | 4 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-08 | Closed | ENHANCEMENT | Rohit Singh
QREL-1456 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-04 | Reopened | WIP | Anurag Ajmera
SFTR-556 | Not all phases charged in TTS | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-02-06 | Resolved | ENHANCEMENT | Vinod Kumar
E2-356 | Not all phases charged in TTS | 9 | 0 | 14 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-06 | Resolved | ENHANCEMENT | Abhishek Jain
QREL-1509 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 | Closed | DEFECT | Anurag Ajmera
QREL-1507 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Closed | ANALYSIS | Anju Gupta
E2-355 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-01-31 | Closed | ANALYSIS | Unis Ahmad Beig
PPB-2311 | Not all phases charged in TTS | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-02-07 | Closed | ENHANCEMENT | Abhishek Jain
SFTR-386 | Not all phases charged in TTS | 0 | 0 | 0 | 4 | 7 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-14 | 2019-02-01 | Resolved | ENHANCEMENT | Ajay Chhillar
INQ-837 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-24 | 2019-02-08 | Open | BACKLOG | Anurag Ajmera
QREL-1465 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Anju Gupta
INQ-715 |  | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-03 | 2019-02-01 | Open | BACKLOG | Peer Hasan Ansari
SFTR-388 |  | 13 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-14 | In Progress | WIP | Arjun Singh
SFTR-387 |  | 17 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-22 | Open | WIP | Vinod Kumar
QREL-1340 |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-08 | 2019-02-06 | Open | BACKLOG | Unis Ahmad Beig
INQ-717 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-07 | Closed | ANALYSIS | Rohit Singh
SFTR-548 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-21 | 2019-02-13 | Closed | ANALYSIS | Arjun Singh
INQ-950 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-11 | Open | WIP | Robina Dhingra
INQ-675 | Opened since november. Reason? | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-11-29 | 2019-02-15 | In Progress | BACKLOG | Rohit Singh
QREL-1506 | Not all phases charged in TTS | 2 | 0 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 | Resolved | ENHANCEMENT | Unis Ahmad Beig
E2-350 | Not all phases charged in TTS | 0 | 0 | 9 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-17 | 2019-02-08 | Closed | ENHANCEMENT | Unis Ahmad Beig
QREL-1501 | Not all phases charged in TTS | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-15 | Resolved | ENHANCEMENT | Alok Tripathi
QREL-1468 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Anju Gupta
QREL-1502 | Not all phases charged in TTS | 3 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-15 | Resolved | ENHANCEMENT | Anju Gupta
INQ-953 |  | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-13 | Closed | ANALYSIS | Priyatosh Kashyap
SFTR-543 | Not all phases charged in TTS | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-24 | 2019-02-06 | Resolved | ENHANCEMENT | Rahul Uniyal
QREL-1467 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-07 | Closed | ANALYSIS | Abhishek Jain
QREL-1500 |  | 5 | 0 | 9 | 1.25 | 4 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-18 | 2019-02-21 | Resolved | ENHANCEMENT | Anju Gupta
TIP-118 | Not all phases charged in TTS | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-24 | 2019-01-29 | Resolved | ENHANCEMENT | Anju Gupta
SFTR-408 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-17 | 2019-01-29 | Resolved | ANALYSIS | Arjun Singh
QREL-1473 | Not all phases charged in TTS | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-06 | Resolved | ENHANCEMENT | Anju Gupta
SFTR-410 |  | 5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-12 | Open | WIP | Arjun Singh
QREL-1474 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-11 | Resolved | ANALYSIS | Anju Gupta
SFTR-376 |  | 0 | 0 | 13 | 2 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-13 | Open | WIP | Vinod Kumar
QREL-1471 | Not all phases charged in TTS | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-12 | Closed | ENHANCEMENT | Anju Gupta
SFTR-373 | Not all phases charged in TTS | 0 | 0 | 1 | 0.75 | 0 | 0.25 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-14 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
PPB-2605 | Not all phases charged in TTS | 3 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-15 | 2019-01-30 | Resolved | ENHANCEMENT | Rohit Singh
QREL-1470 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Anju Gupta
INQ-961 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Closed | ANALYSIS | Anurag Ajmera
E2-360 | Not all phases charged in TTS | 4 | 0 | 10 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-12 | Resolved | ENHANCEMENT | Unis Ahmad Beig
QREL-1479 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Anju Gupta
QREL-1477 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Abhishek Jain
QREL-1511 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Closed | ANALYSIS | Priyatosh Kashyap
PPB-2573 |  | 2 | 0 | 2.5 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-24 | 2019-02-06 | Resolved | ENHANCEMENT | Peer Hasan Ansari
QREL-1490 | Not all phases charged in TTS | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Resolved | ENHANCEMENT | Ashish Pandey
PPB-2577 |  | 15 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-18 | Open | WIP | Anju Gupta
PPB-2576 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-19 | Resolved | ANALYSIS | Abhishek Jain
INQ-934 |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-02-01 | Closed | ANALYSIS | Abhishek Jain
QREL-1484 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | Closed | ANALYSIS | Abhishek Jain
INQ-933 |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-01 | In Progress | WIP | Priyatosh Kashyap
QREL-1361 |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-14 | 2019-02-04 | In Progress | BACKLOG | Rohit Singh
QREL-934 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-01 | Closed | ANALYSIS | Abhishek Jain
INQ-939 |  | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-14 | Resolved | ANALYSIS | Priyatosh Kashyap
PPB-2616 | Not all phases charged in TTS | 4 | 0 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2019-01-31 | 2019-02-18 | Resolved | ENHANCEMENT | Anurag Ajmera
SFTR-482 |  | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 2019-01-25 | 2019-02-22 | Open | BACKLOG | Alok Tripathi
QREL-1407 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-28 | Open | WIP | Anurag Ajmera
QREL-1525 | Not all phases charged in TTS | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-22 | 2019-02-22 | Resolved | ENHANCEMENT | Arjun Singh
SFTR-522 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-18 | 2019-01-31 | Closed | DEFECT | Vinod Kumar
INQ-898 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-23 | 2019-01-29 | In Progress | BACKLOG | Abhishek Jain
QREL-1488 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Open | WIP | Anju Gupta
QREL-1489 | Not all phases charged in TTS | 6 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-12 | 2019-02-13 | Resolved | ENHANCEMENT | Unis Ahmad Beig
SFTR-402 | Not all phases charged in TTS | 4 | 0 | 7 | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-02-01 | Resolved | ENHANCEMENT | Arjun Singh
QREL-1368 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-23 | 2019-01-29 | Closed | DEFECT | Ashish Pandey
SFTR-629 |  | 4 | 0 | 12 | 0.75 | 4 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-22 | Resolved | ENHANCEMENT | Ajay Chhillar
QREL-1419 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-25 | 2019-01-28 | Closed | ANALYSIS | Anurag Ajmera
PPB-2584 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-30 | In Progress | WIP | Anju Gupta
PPB-2622 | Not all phases charged in TTS | 0 | 0 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-18 | Resolved | ENHANCEMENT | Abhishek Jain
PPB-2586 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-13 | In Progress | WIP | Rohit Singh
PPB-2625 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-28 | Open | WIP | Anju Gupta
QREL-1495 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-22 | 2019-02-22 | Open | WIP | Abhishek Jain
SFTR-630 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Resolved | ANALYSIS | Vinod Kumar
PPB-2503 | Not all phases charged in TTS | 24 | 0 | 9 | 6 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2019-02-05 | 2019-02-20 | Resolved | ENHANCEMENT | Abhishek Jain
NA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.5 | 0 | 51.5 | 45.5 | 0 | 20.5 | 2018-11-26 | 2019-02-22 | Open | SUPPORT | Anurag Ajmera
QREL-1372 | Not all phases charged in TTS | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Resolved | ENHANCEMENT | Ashish Pandey
PPB-2509 | Not all phases charged in TTS | 10 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-14 | 2019-02-22 | Resolved | ENHANCEMENT | Kavita Bais
QREL-429 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-11-28 | 2019-02-20 | Open | BAU | Priyatosh Kashyap
PPB-2506 |  | 27 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-12 | 2019-02-22 | Open | WIP | Robina Dhingra
PPB-2507 | Not all phases charged in TTS | 0 | 0 | 9 | 1.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-21 | 2019-02-04 | Resolved | ENHANCEMENT | Rohit Singh
PPB--2616 | Correct ticket ID in TTS. It should be PPB-2616 I believe. | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-01-30 | Resolved | ENHANCEMENT | Anju Gupta
INQ-942 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-08 | In Progress | WIP | Abhishek Jain
QREL-1411 | Not all phases charged in TTS | 6 | 0 | 11 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-25 | 2019-02-14 | Closed | ENHANCEMENT | Priyatosh Kashyap
SFTR-479 | Not all phases charged in TTS | 2 | 0 | 16 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-02-01 | Resolved | ENHANCEMENT | Arjun Singh
N/A |  | 0 | 0 | 0 | 0 | 0 | 0 | 171 | 0 | 27 | 0 | 0 | 0 | 0 | 19 | 2018-11-26 | 2019-02-22 | Open | SUPPORT | Kavita Bais
SFTR-618 | Not all phases charged in TTS | 3 | 0 | 0 | 0.75 | 9 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-21 | Resolved | ENHANCEMENT | Vinod Kumar
QREL-1391 | Not all phases charged in TTS | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-01-30 | Resolved | ENHANCEMENT | Unis Ahmad Beig
PPB-2633 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-04 | Open | WIP | Abhishek Jain
PPB-2234 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-21 | 2019-02-21 | In Progress | WIP | Abhishek Jain
PPB-2510 | Not all phases charged in TTS | 16 | 0 | 101 | 0 | 18 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-24 | 2019-02-19 | Resolved | ENHANCEMENT | Kavita Bais
INQ-913 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-29 | Open | WIP | Priyatosh Kashyap
SFTR-341 | Not all phases charged in TTS | 0 | 0 | 11 | 1 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-22 | 2019-01-31 | Resolved | ENHANCEMENT | Peer Hasan Ansari
QREL-1385 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-29 | Closed | ANALYSIS | Anurag Ajmera
SFTR-586 | Not all phases charged in TTS | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-06 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
SFTR-585 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-01-31 | Closed | DEFECT | Rahul Uniyal
PPB-2517 | Not all phases charged in TTS | 4 | 0 | 68 | 7 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-18 | Resolved | ENHANCEMENT | Abhishek Jain
PPB-2638 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-06 | Open | WIP | Peer Hasan Ansari
SFTR-582 | Not all phases charged in TTS | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-20 | Resolved | ENHANCEMENT | Vinod Kumar
QREL-1382 | Not all phases charged in TTS | 5 | 0 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-29 | Closed | ENHANCEMENT | Anju Gupta
SFTR-460 | Not all phases charged in TTS | 0 | 0 | 5 | 0.75 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-21 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
BAU-2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 2018-12-10 | 2019-02-22 | Open | BAU | Ajay Chhillar
BAU-3 |  | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 2018-11-26 | 2019-02-19 | Open | SUPPORT | Arjun Singh
INQ-910 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-28 | Resolved | ANALYSIS | Rohit Singh
QREL-1425 | Not all phases charged in TTS | 23 | 0 | 6 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-02-11 | Resolved | ENHANCEMENT | Rohit Singh
BAU-5 |  | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-07 | Open | SUPPORT | Priyatosh Kashyap
SFTR-622 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-15 | 2019-02-15 | Open | WIP | Rahul Uniyal
SFTR-607 |  | 9 | 0 | 12 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-12 | In Progress | WIP | Peer Hasan Ansari
SFTR-606 | Not all phases charged in TTS | 0 | 0 | 0 | 0.75 | 0 | 0.25 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-15 | Resolved | ENHANCEMENT | Vinod Kumar
SFTR-608 |  | 13 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-12 | 2019-02-22 | Open | WIP | Rahul Uniyal
PPB-2643 | Not all phases charged in TTS | 2 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-19 | 2019-02-22 | Resolved | ENHANCEMENT | Abhishek Jain
PPB-2642 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-13 | Open | WIP | Unis Ahmad Beig
QREL-1431 |  | 14 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-05 | 2019-02-18 | Open | WIP | Ashish Pandey
SFTR-330 |  | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-07 | 2019-02-13 | In Progress | WIP | Ajay Chhillar
QREL-1432 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-01-30 | Closed | ANALYSIS | Anurag Ajmera
(blank) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 11 | 0 | 0 | 0 | 2018-11-29 | 2019-02-22 | Open | SUPPORT | Ashish Pandey
SFTR-575 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-28 | Closed | DEFECT | Vinod Kumar
QREL-1430 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-29 | Resolved | ANALYSIS | Abhishek Jain
PPB-2646 | Not all phases charged in TTS | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-20 | 2019-02-20 | Resolved | ENHANCEMENT | Arjun Singh
QREL-1394 | Not all phases charged in TTS | 0 | 0 | 14 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-25 | 2019-02-15 | Closed | ENHANCEMENT | Unis Ahmad Beig
INQ-928 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-01-31 | Open | WIP | Anju Gupta
PPB-2529 | Not all phases charged in TTS | 0 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-09 | 2019-01-29 | Resolved | ENHANCEMENT | Rohit Singh
QREL-1439 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-31 | 2019-02-05 | Resolved | DEFECT | Ashish Pandey
SFTR-613 | Not all phases charged in TTS | 0 | 0 | 6 | 2.75 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-13 | 2019-02-14 | Resolved | ENHANCEMENT | Arjun Singh
QREL-1437 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-01 | 2019-02-04 | Open | WIP | Anurag Ajmera
QREL-1438 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-29 | 2019-01-29 | Closed | ANALYSIS | Anurag Ajmera
SFTR-615 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-14 | 2019-02-14 | Closed | ANALYSIS | Arjun Singh
SFTR-610 |  | 9 | 0 | 14 | 0.75 | 4 | 0.25 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-20 | Resolved | ENHANCEMENT | Ajay Chhillar
SFTR-335 | Not all phases charged in TTS | 0 | 0 | 12 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-21 | 2019-01-30 | Resolved | ENHANCEMENT | Peer Hasan Ansari
SFTR-576 | Not all phases charged in TTS | 2 | 0 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-28 | 2019-01-30 | Resolved | ENHANCEMENT | Ajay Chhillar
QREL-1436 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-01-30 | 2019-01-30 | Closed | ANALYSIS | Anurag Ajmera
INQ-920 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-08 | 2019-02-08 | In Progress | WIP | Rohit Singh
SFTR-612 | Not all phases charged in TTS | 0 | 0 | 9 | 0.75 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-11 | 2019-02-12 | Resolved | ENHANCEMENT | Vinod Kumar
INQ-886 | Not all phases charged in TTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2019-01-22 | 2019-02-14 | Closed | ENHANCEMENT | Rohit Singh
SFTR-579 |  | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-18 | 2019-02-21 | Open | WIP | Vinod Kumar
QREL-1434 | Not all phases charged in TTS | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-04 | 2019-02-05 | Closed | ENHANCEMENT | Peer Hasan Ansari
SFTR-611 |  | 6 | 0 | 12 | 0.75 | 8 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-02-14 | 2019-02-19 | Resolved | ENHANCEMENT | Ajay Chhillar
Redirected Tickets

## Defect Reconciliation
TTS Ticket ID | TTS Rework Effort | Defect Log Rework | TTS Type | Effort Match | Error
PPB-2650 | 0 | #N/A | WIP
PPB-2530 | 0 | #N/A | WIP
PPB-2376 | 0 | #N/A | WIP
PPB-2653 | 0 | #N/A | WIP
PPB-2416 | 0 | #N/A | ENHANCEMENT
SFTR-561 | 1 | #N/A | DEFECT |  | Not found in defect log
QREL-1440 | 0 | #N/A | ENHANCEMENT
SFTR-564 | 0 | #N/A | ENHANCEMENT
PPB-2415 | 0 | #N/A | ENHANCEMENT
QREL-1441 | 0 | #N/A | ENHANCEMENT
SFTR-563 | 9 | #N/A | DEFECT |  | Not found in defect log
QREL-1285 | 0 | #N/A | BACKLOG
SFTR-569 | 6 | #N/A | DEFECT |  | Not found in defect log
QREL-1449 | 0 | #N/A | ENHANCEMENT
SFTR-329 | 0 | #N/A | ENHANCEMENT
QREL-1446 | 0 | #N/A | ENHANCEMENT
SFTR-566 | 0 | #N/A | ANALYSIS
SFTR-565 | 0 | #N/A | ENHANCEMENT
QREL-1444 | 0 | #N/A | ENHANCEMENT
SFTR-568 | 6 | #N/A | DEFECT |  | Not found in defect log
QREL-1445 | 0 | #N/A | ENHANCEMENT
SFTR-567 | 5 | #N/A | DEFECT |  | Not found in defect log
PPB-2422 | 0 | #N/A | ENHANCEMENT
QREL-1453 | 1 | 1 | ENHANCEMENT | TRUE
PPB-2548 | 0 | #N/A | WIP
SFTR-551 | 1 | #N/A | ENHANCEMENT
QREL-1451 | 0 | #N/A | ENHANCEMENT
SFTR-311 | 4 | #N/A | ENHANCEMENT
SFTR-553 | 3 | #N/A | DEFECT |  | Not found in defect log
SFTR-399 | 0 | #N/A | ENHANCEMENT
QREL-1452 | 1 | 1 | ENHANCEMENT | TRUE
SFTR-552 | 0 | #N/A | ANALYSIS
SFTR-398 | 0 | #N/A | ENHANCEMENT
SFTR-394 | 0 | #N/A | WIP
QREL-1458 | 4 | 4 | DEFECT | TRUE
SFTR-554 | 9 | #N/A | DEFECT |  | Not found in defect log
TIP-108 | 0 | #N/A | BACKLOG
QREL-1455 | 0 | #N/A | ENHANCEMENT
QREL-1456 | 4 | 4 | WIP | TRUE
SFTR-556 | 9 | #N/A | ENHANCEMENT
E2-356 | 0 | #N/A | ENHANCEMENT
QREL-1509 | 4 | 4 | DEFECT | TRUE
QREL-1507 | 0 | #N/A | ANALYSIS
E2-355 | 0 | #N/A | ANALYSIS
PPB-2311 | 0 | #N/A | ENHANCEMENT
SFTR-386 | 3 | #N/A | ENHANCEMENT
INQ-837 | 0 | #N/A | BACKLOG
QREL-1465 | 0 | #N/A | ANALYSIS
INQ-715 | 0 | #N/A | BACKLOG
SFTR-388 | 0 | #N/A | WIP
SFTR-387 | 0 | #N/A | WIP
QREL-1340 | 0 | #N/A | BACKLOG
INQ-717 | 0 | #N/A | ANALYSIS
SFTR-548 | 0 | #N/A | ANALYSIS
INQ-950 | 0 | #N/A | WIP
INQ-675 | 0 | #N/A | BACKLOG
QREL-1506 | 0 | #N/A | ENHANCEMENT
E2-350 | 0 | #N/A | ENHANCEMENT
QREL-1501 | 0 | #N/A | ENHANCEMENT
QREL-1468 | 0 | #N/A | ANALYSIS
QREL-1502 | 0 | #N/A | ENHANCEMENT
INQ-953 | 0 | #N/A | ANALYSIS
SFTR-543 | 0 | #N/A | ENHANCEMENT
QREL-1467 | 0 | #N/A | ANALYSIS
QREL-1500 | 0 | #N/A | ENHANCEMENT
TIP-118 | 0 | #N/A | ENHANCEMENT
SFTR-408 | 0 | #N/A | ANALYSIS
QREL-1473 | 0 | #N/A | ENHANCEMENT
SFTR-410 | 0 | #N/A | WIP
QREL-1474 | 0 | #N/A | ANALYSIS
SFTR-376 | 1 | #N/A | WIP
QREL-1471 | 3 | #N/A | ENHANCEMENT
SFTR-373 | 1 | #N/A | ENHANCEMENT
PPB-2605 | 1 | #N/A | ENHANCEMENT
QREL-1470 | 0 | #N/A | ANALYSIS
INQ-961 | 0 | #N/A | ANALYSIS
E2-360 | 0 | #N/A | ENHANCEMENT
QREL-1479 | 0 | #N/A | ANALYSIS
QREL-1477 | 0 | #N/A | ANALYSIS
QREL-1511 | 0 | #N/A | ANALYSIS
PPB-2573 | 0 | #N/A | ENHANCEMENT
QREL-1490 | 0 | #N/A | ENHANCEMENT
PPB-2577 | 0 | #N/A | WIP
PPB-2576 | 0 | #N/A | ANALYSIS
INQ-934 | 0 | #N/A | ANALYSIS
QREL-1484 | 0 | #N/A | ANALYSIS
INQ-933 | 0 | #N/A | WIP
QREL-1361 | 0 | #N/A | BACKLOG
QREL-934 | 0 | #N/A | ANALYSIS
INQ-939 | 0 | #N/A | ANALYSIS
PPB-2616 | 0 | #N/A | ENHANCEMENT
SFTR-482 | 0 | #N/A | BACKLOG
QREL-1407 | 0 | #N/A | WIP
QREL-1525 | 0 | #N/A | ENHANCEMENT
SFTR-522 | 24 | #N/A | DEFECT |  | Not found in defect log
INQ-898 | 0 | #N/A | BACKLOG
QREL-1488 | 0 | #N/A | WIP
QREL-1489 | 2 | 2 | ENHANCEMENT | TRUE
SFTR-402 | 0 | #N/A | ENHANCEMENT
QREL-1368 | 18 | #N/A | DEFECT |  | Not found in defect log
SFTR-629 | 0 | #N/A | ENHANCEMENT
QREL-1419 | 0 | #N/A | ANALYSIS
PPB-2584 | 0 | #N/A | WIP
PPB-2622 | 0 | #N/A | ENHANCEMENT
PPB-2586 | 0 | #N/A | WIP
PPB-2625 | 0 | #N/A | WIP
QREL-1495 | 0 | #N/A | WIP
SFTR-630 | 0 | #N/A | ANALYSIS
PPB-2503 | 0 | #N/A | ENHANCEMENT
NA | 0 | #N/A | SUPPORT
QREL-1372 | 0 | #N/A | ENHANCEMENT
PPB-2509 | 0 | #N/A | ENHANCEMENT
QREL-429 | 0 | #N/A | BAU
PPB-2506 | 0 | #N/A | WIP
PPB-2507 | 0 | #N/A | ENHANCEMENT
PPB--2616 | 0 | #N/A | ENHANCEMENT
INQ-942 | 0 | #N/A | WIP
QREL-1411 | 0 | #N/A | ENHANCEMENT
SFTR-479 | 0 | #N/A | ENHANCEMENT
N/A | 0 | #N/A | SUPPORT
SFTR-618 | 0 | #N/A | ENHANCEMENT
QREL-1391 | 0 | #N/A | ENHANCEMENT
PPB-2633 | 0 | #N/A | WIP
PPB-2234 | 0 | #N/A | WIP
PPB-2510 | 8 | 1 | ENHANCEMENT | FALSE | TTS Effort (8 hrs) does not match defect log effort (1 hr)
INQ-913 | 0 | #N/A | WIP
SFTR-341 | 0 | #N/A | ENHANCEMENT
QREL-1385 | 0 | #N/A | ANALYSIS
SFTR-586 | 0 | #N/A | ENHANCEMENT
SFTR-585 | 4 | #N/A | DEFECT |  | Not found in defect log
PPB-2517 | 0 | #N/A | ENHANCEMENT
PPB-2638 | 0 | #N/A | WIP
SFTR-582 | 0 | #N/A | ENHANCEMENT
QREL-1382 | 0 | #N/A | ENHANCEMENT
SFTR-460 | 0 | #N/A | ENHANCEMENT
BAU-2 | 0 | #N/A | BAU
BAU-3 | 0 | #N/A | SUPPORT
INQ-910 | 0 | #N/A | ANALYSIS
QREL-1425 | 0 | #N/A | ENHANCEMENT
BAU-5 | 0 | #N/A | SUPPORT
SFTR-622 | 9 | #N/A | WIP
SFTR-607 | 0 | #N/A | WIP
SFTR-606 | 4 | #N/A | ENHANCEMENT
SFTR-608 | 0 | #N/A | WIP
PPB-2643 | 0 | #N/A | ENHANCEMENT
PPB-2642 | 0 | #N/A | WIP
QREL-1431 | 0 | #N/A | WIP
SFTR-330 | 0 | #N/A | WIP
QREL-1432 | 0 | #N/A | ANALYSIS
(blank) | 0 | #N/A | SUPPORT
SFTR-575 | 2 | #N/A | DEFECT |  | Not found in defect log
QREL-1430 | 0 | #N/A | ANALYSIS
PPB-2646 | 0 | #N/A | ENHANCEMENT
QREL-1394 | 0 | #N/A | ENHANCEMENT
INQ-928 | 0 | #N/A | WIP
PPB-2529 | 0 | #N/A | ENHANCEMENT
QREL-1439 | 26 | #N/A | DEFECT |  | Not found in defect log
SFTR-613 | 0 | #N/A | ENHANCEMENT
QREL-1437 | 4 | 4 | WIP | TRUE
QREL-1438 | 0 | #N/A | ANALYSIS
SFTR-615 | 0 | #N/A | ANALYSIS
SFTR-610 | 4 | #N/A | ENHANCEMENT
SFTR-335 | 0 | #N/A | ENHANCEMENT
SFTR-576 | 0 | #N/A | ENHANCEMENT
QREL-1436 | 0 | #N/A | ANALYSIS
INQ-920 | 0 | #N/A | WIP
SFTR-612 | 0 | #N/A | ENHANCEMENT
INQ-886 | 0 | #N/A | ENHANCEMENT
SFTR-579 | 0 | #N/A | WIP
QREL-1434 | 11 | #N/A | ENHANCEMENT
SFTR-611 | 0 | #N/A | ENHANCEMENT

## Defect Log for given period
Defect No. | ID | Month | Dev Release / Component | Maint Release / Component | Testing Release / Component | Task ID | Brief Description of Defect (Includes steps to reproduce ) | Defect Source | Type of Review/ Test | Date Raised (DD-MMM-YY) | Reported By | Fixed By | Date Fixed (DD-MMM-YY) | Verified By | Rework Effort
QREL-147 | QREL-147 | February | Report 2.1 |  |  | QREL-1471 | Jurisdiction is still not updated for CANC | External (Customer reported) defect | Functional Testing | 43508 | Sandeep Reddy | Anju Gupta | 43508 | Abhishek Jain | 4 | Row Labels | Sum of Rework Effort | Defect Log ID | DL Rework | TTS Presence
DEV_MA_562 | QREL-1489 | February | Report 2.1 |  |  | QREL-1489 | Enum value was not converted due t which incorrect NCA was getting displayed | Internal Review & Testing defect | Unit Testing | 43508 | Anju Gupta | Anju Gupta | 43508 | Anju Gupta | 2 | APAReport-201 | 0 | APAReport-201 | 0 | #N/A
DEV_MA_563 | QREL-1453 | February | Report 2.1 |  |  | QREL-1453 | Checked with wrong position for executing entity | Internal Review & Testing defect | Unit Testing | 43501 | Anju Gupta | Anju Gupta | 43501 | Anju Gupta | 1 | INS-78 | 0 | INS-78 | 0 | #N/A
DEV_MA_564 | QREL-1452 | February | Report 2.1 |  |  | QREL-1452 | Trasaction got rejecte icnorreclty due to incorrect logic | Internal Review & Testing defect | Unit Testing | 43503 | Anju Gupta | Anju Gupta | 43503 | Anju Gupta | 1 | PPB-2510 | 1 | PPB-2510 | 1 | 8
DEV_MA_565 | SFTR-379 | February | SFTR1.2.2 |  |  | SFTR-379 | RPD instruction is not feched correctly sometimes | Internal Review & Testing defect | Unit Testing | 43509 | Vinod Kumar | Vinod kumar | 43509 | Vinod Kumar | 0.25 | QREL-1437 | 4 | QREL-1437 | 4 | 4
DEV_MA_566 | SFTR-379 | February | SFTR1.2.2 |  |  | SFTR-379 | LifeCyckle events not populated in events | Internal Review & Testing defect | Unit Testing | 43509 | Vinod Kumar | Vinod kumar | 43509 | Vinod Kumar | 0.25 | QREL-1452 | 1 | QREL-1452 | 1 | 1
DEV_MA_567 | SFTR-379 | February | SFTR1.2.2 |  |  | SFTR-379 | iTests Coverage needs to be increased | Internal Review & Testing defect | Unit Testing | 43509 | Vinod Kumar | Vinod kumar | 43509 | Vinod Kumar | 0.25 | QREL-1453 | 1 | QREL-1453 | 1 | 1
DEV_MA_568 | SFTR-379 | February | SFTR1.2.2 |  |  | SFTR-379 | junit test for feaching last RPD instruction | Internal Review & Testing defect | Unit Testing | 43509 | Vinod Kumar | Vinod kumar | 43509 | Vinod Kumar | 0.25 | QREL-1456 | 4 | QREL-1456 | 4 | 4
DEV_MA_569 | PPB-2510 | February | Report 2.2.0 |  |  | PPB-2510 | File getting QUEUED with database exception when TRAX_ID sent with more than 50 characters | Internal Review & Testing defect | Unit Testing | 43515 | Kavita Bais | Kavita Bais | 43515 | Anju Gupta | 0.25 | QREL-1458 | 4 | QREL-1458 | 4 | 4
DEV_MA_570 | PPB-2510 | February | Report 2.2.0 |  |  | PPB-2510 | Syntax error shown for Term of contract value only | Internal Review & Testing defect | Unit Testing | 43515 | Kavita Bais | Kavita Bais | 43515 | Anju Gupta | 0.25 | QREL-147 | 4 | QREL-147 | 4 | #N/A
DEV_MA_571 | PPB-2510 | February | Report 2.2.0 |  |  | PPB-2510 | Rejection Reason coming blank as not set for Term of contract | Internal Review & Testing defect | Unit Testing | 43515 | Kavita Bais | Kavita Bais | 43515 | Anju Gupta | 0.25 | QREL-1489 | 2 | QREL-1489 | 2 | 2
DEV_MA_572 | PPB-2510 | February | Report 2.2.0 |  |  | PPB-2510 | Fixed existing Uts which were getting failed because of new added field | Internal Review & Testing defect | Unit Testing | 43515 | Kavita Bais | Kavita Bais | 43515 | Anju Gupta | 0.25 | QREL-1509 | 4 | QREL-1509 | 4 | 4
QREL-1456 | QREL-1456 | February | APA2.1.0 |  |  | QREL-1456 | Package trade amend issue | External (Customer reported) defect | Functional Testing | 43499 | Hemalatha Subramanian |  |  | Anurag Ajmera | 4 | report-1112 | 0 | report-1112 | 0 | #N/A
QREL-1437 | QREL-1437 | February | APA2.1.0 |  |  | QREL-1437 | Trade size calculation | External (Customer reported) defect | Functional Testing | 43499 | Ashish Chikle |  |  | Anurag Ajmera | 4 | report-1123 | 0 | report-1123 | 0 | #N/A
QREL-1458 | QREL-1458 | February | APA2.1.0 |  |  | QREL-1458 | Aggregate job issue | External (Customer reported) defect | Functional Testing | 43500 | Hemalatha Subramanian |  |  | Anurag Ajmera | 4 | report-1132 | 0 | report-1132 | 0 | #N/A
QREL-1509 | QREL-1509 | February | APA2.1.0 |  |  | QREL-1509 | Publication schedule issue | External (Customer reported) defect | Functional Testing | 43514 | Hemalatha Subramanian |  |  | Anurag Ajmera | 4 | SFTR-139 | 0 | SFTR-139 | 0 | #N/A
APAReport-201 | PPB-2416 | February |  |  |  | PPB-2416 | Wouldn't this condition be okay, if we'd written it like this {code} AND SI_ACCUMULATION_GROUPS.MIFID_ASSET_CLASS = INSTRUMENT.MIFID_ASSET_CLASS AND (SI_ACCUMULATION_GROUPS.SUB_ASSET_CLASS = INSTRUMENT.SUB_ASSET_CLASS OR SI_ACCUMULATION_GROUPS.SUB_ASSET_CLASS IN ('N/A','All')) {code} | Internal Review & Testing defect | Code Review | 43504 | Priyatosh Kashyap | Robina Dhingra | 43504 | Priyatosh Kashyap | 0 | SFTR-144 | 0 | SFTR-144 | 0 | #N/A
APAReport-201 | PPB-2416 | February |  |  |  | PPB-2416 | NVL handling has been removed from the EXCH_RATE, in this query. It exists in the query above it | Internal Review & Testing defect | Code Review | 43504 | Priyatosh Kashyap | Robina Dhingra | 43504 | Priyatosh Kashyap | 0 | SFTR-150 | 0 | SFTR-150 | 0 | #N/A
APAReport-201 | PPB-2416 | February |  |  |  | PPB-2416 | The Parameter IS_EQTY was removed in the new query | Internal Review & Testing defect | Code Review | 43504 | Priyatosh Kashyap | Robina Dhingra | 43504 | Priyatosh Kashyap | 0 | SFTR-151 | 0 | SFTR-151 | 0 | #N/A
SFTR-150 | SFTR-150 | February |  |  |  | SFTR-564 | we are not really happy with the Chris proposed change of colors on the statuses, not even Nick is, and its not consistent. Were does this change comes from? | Internal Review & Testing defect | Code Review | 43503 | Rodrigo Jaen | Ashish Pandey | 43503 | Rodrigo Jaen | 0 | SFTR-153 | 0 | SFTR-153 | 0 | #N/A
report-1123 | report-1123 | February |  |  |  | QREL-1446 | no changes are required in itests for this change? | Internal Review & Testing defect | Code Review | 43508 | Abhishek Jain | Anju Gupta | 43508 | Abhishek Jain | 0 | SFTR-159 | 0 | SFTR-159 | 0 | #N/A
SFTR-151 | SFTR-151 | February |  |  |  | SFTR-311 | Please ensure the grouping work fine as expected when LEI is null or internal code is null for multiple values (internal codes and leis respectively). | Internal Review & Testing defect | Code Review | 43504 | Vinod Kumar | Ajay Chhillar | 43504 | Vinod Kumar | 0 | SFTR-165 | 0 | SFTR-165 | 0 | #N/A
SFTR-151 | SFTR-151 | February |  |  |  | SFTR-311 | Please add the table in roll back schema sql as well | Internal Review & Testing defect | Code Review | 43504 | Vinod Kumar | Ajay Chhillar | 43504 | Vinod Kumar | 0 | SFTR-379 | 1 | SFTR-379 | 1 | #N/A
SFTR-151 | SFTR-151 | February |  |  |  | SFTR-311 | Use SftrIntegrationTest instead o ES if we don't need to test ES feature. | Internal Review & Testing defect | Code Review | 43504 | Vinod Kumar | Ajay Chhillar | 43504 | Vinod Kumar | 0 | Grand Total | 26
SFTR-144 | SFTR-144 | February |  |  |  | SFTR-543 | Add only one method for currency validation. Remove other method which include null. null condition should be taken care by original method. Also, d the same thing for Enum util. | Internal Review & Testing defect | Code Review | 43502 | Vinod Kumar | Rahul Uniyal | 43502 | Vinod Kumar | 0
report-1132 | report-1132 | February |  |  |  | QREL-1500 | Please check that it is supported on both the formats - normal download and download in upload format. | Internal Review & Testing defect | Code Review | 43515 | Abhishek Jain | Unis Beig | 43515 | Abhishek Jain | 0
report-1112 | report-1112 | February |  |  |  | QREL-1473 | please add test file. | Internal Review & Testing defect | Code Review | 43502 | Abhishek Jain | Anju Gupta | 43502 | Abhishek Jain | 0
report-1112 | report-1112 | February |  |  |  | QREL-1473 | Please provide a script to update all the impacted transactions in prod. | Internal Review & Testing defect | Code Review | 43502 | Abhishek Jain | Anju Gupta | 43502 | Abhishek Jain | 0
INS-78 | INS-78 | February |  |  |  | SFTR-482 | don't we have a custom component for this on insight-commons?, we have other upload to build, so if we do not have the component maybe its worth adding it | Internal Review & Testing defect | Code Review | 43508 | Rodrigo Jaen | Alok Tripathi | 43508 | Rodrigo Jaen | 0
INS-78 | INS-78 | February |  |  |  | SFTR-482 | how is this customizable? | Internal Review & Testing defect | Code Review | 43508 | Rodrigo Jaen | Alok Tripathi | 43508 | Rodrigo Jaen | 0
INS-78 | INS-78 | February |  |  |  | SFTR-482 | this rules about file size, file name length need to be configurable as not all the applications follow the same. | Internal Review & Testing defect | Code Review | 43508 | Rodrigo Jaen | Alok Tripathi | 43508 | Rodrigo Jaen | 0
SFTR-165 | SFTR-165 | February |  |  |  | SFTR-629 | LEI or internal code, report type should be mandatory for this request. | Internal Review & Testing defect | Code Review | 43517 | Vinod Kumar | Ajay Chhillar | 43517 | Vinod Kumar | 0
SFTR-165 | SFTR-165 | February |  |  |  | SFTR-629 | Please pass payload type key in this method to avoid fetching it from list in called method. | Internal Review & Testing defect | Code Review | 43517 | Vinod Kumar | Ajay Chhillar | 43517 | Vinod Kumar | 0
SFTR-165 | SFTR-165 | February |  |  |  | SFTR-629 | Any particular reason to use a string rather than define a shared constant? i.e. Transaction" should really be defined as a constant and used globally Same for Margin and ReUse " | Internal Review & Testing defect | Code Review | 43516 | Chris Dickinson | Ajay Chhillar | 43516 | Chris Dickinson | 0
SFTR-139 | SFTR-139 | February |  |  |  | SFTR-479 | Use messageId instead of UNKNOWN column in ingestion files. | Internal Review & Testing defect | Code Review | 43497 | Vinod Kumar | Arjun Singh | 43497 | Vinod Kumar | 0
SFTR-159 | SFTR-159 | February |  |  |  | SFTR-613 | Last column in the rules sheet is repeating for every entry. Please club it with single condition as in other sheets. | Internal Review & Testing defect | Code Review | 43510 | Vinod Kumar | Arjun Singh | 43510 | Vinod Kumar | 0
SFTR-153 | SFTR-153 | February |  |  |  | SFTR-610 | please provide meaning full comments or remove logs. | Internal Review & Testing defect | Code Review | 43508 | Vinod Kumar | Ajay Chhillar | 43508 | Vinod Kumar | 0
SFTR-153 | SFTR-153 | February |  |  |  | SFTR-610 | Dont pass exhcnage object. Just get User from exchange and pass user or executing firms. | Internal Review & Testing defect | Code Review | 43508 | Vinod Kumar | Ajay Chhillar | 43508 | Vinod Kumar | 0

## error owners
Name | Confirmed?
Alok Tripathi
Ashish Pandey | done
Priyatosh Kashyap | delegated to robina/abhishek
Unis Ahmad Beig
Abhishek Jain
Vinod Kumar
Anju Gupta
Ajay Chhillar
Rahul Uniyal
Rohit Singh
Rohit Singh/Abhishek Jain
Anurag Ajmera
Arjun Singh
Kavita Bais
Peer Hasan Ansari | done

## Redirected Tickets
Actual | Redirected
INQ-837 | PPB-2657
INQ-715 | PPB-2638
QREL-1340 | PPB-2642
INQ-950 | PPB-2659
INQ-928 | PPB-2632